## Sheet1
num | act | Activity | Cohort | Climate zone | Label | Label2 | Label3 | Label4 | Start | Finish
1 | 1.1.2 | Professional development instruments and models |  |  | 35 Master Trainers and 7 Teacher Educators trained | 35 Master Trainers and 7 Teacher Educators trained | 35 Master Trainers | 35 | 2024-11-01 | 2025-01-01
2 | 1.1.4 | Teachers trained on UNICEF Package | 1 | Warm | Cohort 1, Year 1, Warm Climate | 400 CBE / 2,625 teachers trained | 400 CBE / 2,625 teachers | 3025 | 2024-05-01 | 2024-09-01
3 | 1.1.4 | Teachers trained on UNICEF Package | 1 | Cold | Cohort 1, Year 2, Cold Climate | 400 CBE / 2,625 teachers trained | 400 CBE / 2,625 teachers | 3025 | 2024-12-01 | 2025-04-01
4 | 1.1.4 | Teachers trained on UNICEF Package | 2 | Warm | Cohort 2, Year 3, Warm Climate | 400 CBE / 2,625 teachers trained | 400 CBE / 2,625 teachers | 3025 | 2026-05-01 | 2026-09-01
5 | 1.1.4 | Teachers trained on UNICEF Package | 2 | Cold | Cohort 2, Year 4, Cold Climate | 400 CBE / 2,625 teachers trained | 400 CBE / 2,625 teachers | 3025 | 2026-12-01 | 2027-04-01
6 | 1.1.8 | Teacher-learner materials | 1 | Warm | Cohort 1, Year 1, Warm Climate | 2,625 teachers / 52,500 students | 2,625 teachers / 52,500 students | 2,625 T / 52,500 S | 2024-05-01 | 2024-09-01
7 | 1.1.8 | Teacher-learner materials | 1 | Cold | Cohort 1, Year 2, Cold Climate | 2,625 teachers / 52,500 students | 2,625 teachers / 52,500 students | 2,625 T / 52,500 S | 2024-12-01 | 2025-04-01
8 | 1.1.8 | Teacher-learner materials | 2 | Warm | Cohort 2, Year 3, Warm Climate | 2,625 teachers / 52,500 students | 2,625 teachers / 52,500 students | 2,625 T / 52,500 S | 2026-05-01 | 2026-09-01
9 | 1.1.8 | Teacher-learner materials | 2 | Cold | Cohort 2, Year 4, Cold Climate | 2,625 teachers / 52,500 students | 2,625 teachers / 52,500 students | 2,625 T / 52,500 S | 2026-12-01 | 2027-04-01
10 | 1.2.1 | Targeted remediation | 1 | Warm | Cohort 1, Year 2 | 1,050 teachers / 10,500 students | 1,050 teachers / 10,500 students | 1,050 T / 10,500 S | 2024-10-01 | 2025-10-01
11 | 1.2.1 | Targeted remediation | 2 | Cold | Cohort 2, Year 4 | 1,050 teachers / 10,500 students | 1,050 teachers / 10,500 students | 1,050 T / 10,500 S | 2026-10-01 | 2027-10-01